## Project Dashboard
OrbitFlow — Project Dashboard ¦ All metrics linked to Work Items
Click Task / Bug / Risk / CR counts to navigate to Work Items filter · EV = SOW Contracted Hrs − Actual Task Effort · SV = Planned End − Max Task/Bug End Date
PROJECT IDENTITY | [5 empty] | PLANNED SCHEDULE |  |  | ACTUALS (from Work Items) |  |  |  |  | WORK ITEMS (click to filter) |  |  |  | RAG STATUS
Project ID | Project Name | PM | Account Manager | Project Type | Status | Planned Start | Planned End | SOW Hrs (Contracted) | Actual Start (Min Task/Bug) | Actual End (Max Task/Bug) | Actual Effort (hrs) | EV Hrs (SOW−Actual) | SV Days (Planned−Actual End) | Tasks (Done / Total) | Bugs (Fixed / Total) | Open Risks | Pending CRs | Schedule RAG | Financial RAG | Overall RAG
TOTALS

## Work Items
OrbitFlow — Work Items (Tasks · Bugs · CRs · Risks)
🔍 Filter by Project: | — All Projects — |  |  |  | ← Select project to highlight rows ¦ Use column filters (▼) to filter data
Quick Stats ▶ |  | Tasks |  | Bugs |  | Risks |  | CRs |  | Orig Hrs |  | Act Hrs
Type | ID | Summary | Module | SubModule | Event / BugType | Category | Activity | Sub-Activity | Assigned To | Priority | Status | Worked Date | Original Effort (hrs) | Actual Effort (hrs) | Start Date | End Date | Probability (1-5) | Impact (1-5) | Mitigation Hrs | Legacy Risk Score | Description | Story Points | Remarks | Completed Date
Task | GCI-T001 | Monthly Support - Case Management & Config | GCI Phase 1 | Case Management | Configure | Support | Development | Coding | Prateek Shinde | P2 | Completed | 2026-07-01 | 80 | 80 | 2026-07-01 | 2026-07-15
Task | GCI-T002 | Monthly Support - Field Service Optimization | GCI Phase 1 | Field Service | Amend | Support | Development | Coding | Sudhakar Reddy Lekkala | P2 | Completed | 2026-07-16 | 80 | 80 | 2026-07-16 | 2026-07-31
Task | GCI-T003 | Monthly Support - API Integration Review | GCI Phase 1 | API Integration | Amend | Support | Development | Coding | Sudhakar Reddy Lekkala | P2 | In Progress | 2026-08-01 | 80 | 60 | 2026-08-01 | 2026-08-31
Task | GCI-T004 | Canada Holiday Buffer - Aug Support Hours | GCI Phase 1 | Support Block | Configure | Support | Development | Coding | Prateek Shinde | P3 | In Progress | 2026-08-15 | 40 | 20 | 2026-08-15 | 2026-08-31
Bug | GCI-B001 | API timeout on bulk sync over 5000 records | GCI Phase 1 | API Integration | Functional | Bug Fix | Resolution | Code Fix | Sudhakar Reddy Lekkala | P2 | Monitoring | 2026-07-20 | 8 | 4 | 2026-07-20 | 2026-08-31
Risk | GCI-RK001 | Timezone Coordination Gap - Canada Team | GCI Phase 1 | Resource Management | Resource Risk | Risk Management | Identification | Risk Logging | Gopikrishna Vemuri | P2 | Open | 2026-07-01 | 8 | 2 | 2026-07-01 | 2026-09-30 |  |  | 8 | 9
Risk | GCI-RK002 | New Client Requirements Mid-Engagement | GCI Phase 1 | Scope Management | Scope Risk | Risk Management | Identification | Risk Logging | Gopikrishna Vemuri | P3 | Open | 2026-07-01 | 4 | 1 | 2026-07-01 | 2026-12-31 |  |  | 4 | 8
CR | GCI-CR001 | Canada Holiday Buffer Hours | GCI Phase 1 | Support Block | Scope Addition | Change Request | Analysis | Impact Analysis | Gopikrishna Vemuri | P3 | Approved | 2026-07-01 | 40 | 20 | 2026-08-01 | 2026-08-31
Task | CTRL-T001 | Requirements & BRD Review | Control Solutions | Sales Cloud | Analyze | Project Management | Development | Coding | Ester Rani Ganji | P1 | Completed | 2026-06-01 | 12 | 12 | 2026-06-01 | 2026-06-03
Task | CTRL-T002 | Salesforce Org Setup & Config | Control Solutions | Sales Cloud | Configure | Development | Development | Coding | Jeevan Babu Paruchuri | P1 | Completed | 2026-06-04 | 20 | 22 | 2026-06-04 | 2026-06-10
Task | CTRL-T003 | Data Model Design - Custom Objects | Control Solutions | Sales Cloud | Create | Development | Development | Coding | Akhil Kotagiri | P1 | Completed | 2026-06-04 | 32 | 35 | 2026-06-04 | 2026-06-11
Task | CTRL-T004 | Integration Architecture Blueprint | Control Solutions | QB Integration | Analyze | Development | Development | Coding | Sureshkumar Gidugu | P2 | Completed | 2026-06-07 | 20 | 18 | 2026-06-07 | 2026-06-13
Task | CTRL-T005 | Security & Permission Set Design | Control Solutions | Sales Cloud | Configure | Development | Development | Coding | Nagarjuna Reddy Sadhu | P2 | Completed | 2026-06-07 | 12 | 12 | 2026-06-07 | 2026-06-10
Task | CTRL-T006 | FSL Work Orders & Service Appointments | Control Solutions | FSL | Create | Development | Development | Coding | Vishnudeep | P1 | Completed | 2026-06-11 | 32 | 36 | 2026-06-11 | 2026-06-20
Task | CTRL-T007 | Service Cloud Case Management | Control Solutions | Service Cloud | Create | Development | Development | Coding | Seeham Saber Hussain | P1 | Completed | 2026-06-11 | 20 | 20 | 2026-06-11 | 2026-06-17
Task | CTRL-T008 | QB Integration - Design Phase | Control Solutions | QB Integration | Create | Development | Development | Coding | Sureshkumar Gidugu | P1 | In Progress | 2026-06-18 | 32 | 20 | 2026-06-18 | 2026-07-11
Task | CTRL-T009 | UAT Test Plan Creation | Control Solutions | UAT | Create | QA - Testing | Development | Coding | Tejaswini Reddy Tamma | P2 | Completed | 2026-06-15 | 12 | 12 | 2026-06-15 | 2026-06-18
Task | CTRL-T010 | Custom Report Development - 40 hrs | Control Solutions | Reports | Create | Development | Development | Coding | Nagarjuna Reddy Sadhu | P3 | Completed | 2026-06-20 | 40 | 42 | 2026-06-20 | 2026-06-30
Task | CTRL-T011 | UAT Execution & Client Sign-off | Control Solutions | UAT | Test | QA - Testing | Development | Coding | Tejaswini Reddy Tamma | P1 | In Progress | 2026-06-30 | 20 | 10 | 2026-06-30 | 2026-07-11
Task | CTRL-T012 | QB Integration - Development | Control Solutions | QB Integration | Create | Development | Development | Coding | Sureshkumar Gidugu | P1 | Blocked | 2026-06-25 | 52 | 0 | 2026-06-25 | 2026-07-26
Task | CTRL-T013 | Bug Fixes Round 1 | Control Solutions | Sales Cloud | Amend | Development | Development | Coding | Jeevan Babu Paruchuri | P1 | In Progress | 2026-06-30 | 20 | 8 | 2026-06-30 | 2026-07-11
Task | CTRL-T014 | Go-Live Preparation & Checklist | Control Solutions | Deployment | Create | Project Management | Development | Coding | Ester Rani Ganji | P1 | To Do |  | 12 | 0 | 2026-07-12 | 2026-07-18
Task | CTRL-T015 | Production Deployment | Control Solutions | Deployment | Deploy | Development | Development | Coding | Akhil Kotagiri | P1 | To Do |  | 12 | 0 | 2026-07-18 | 2026-07-21
Bug | CTRL-B001 | FSL Work Order not auto-creating Service Appointment | Control Solutions | FSL | Functional | Bug Fix | Resolution | Code Fix | Vishnudeep | P1 | Fixed | 2026-06-18 | 6 | 4 | 2026-06-18 | 2026-06-21
Bug | CTRL-B002 | QB sync creating duplicate invoice records | Control Solutions | QB Integration | Integration Bug | Bug Fix | Resolution | Code Fix | Sureshkumar Gidugu | P1 | In Progress | 2026-06-22 | 8 | 4 | 2026-06-22 | 2026-07-11
Bug | CTRL-B003 | Custom report date filter ignoring timezone offset | Control Solutions | Reports | Functional | Bug Fix | Resolution | Code Fix | Nagarjuna Reddy Sadhu | P3 | Open | 2026-06-28 | 4 | 0 | 2026-06-28 | 2026-07-11
Bug | CTRL-B004 | Permission set missing field access for Service Manager | Control Solutions | Sales Cloud | Config Bug | Bug Fix | Resolution | Code Fix | Akhil Kotagiri | P2 | Fixed | 2026-06-29 | 4 | 3 | 2026-06-29 | 2026-06-30
Risk | CTRL-RK001 | Effort Overrun - 107 Hours | Control Solutions | Financial Management | Financial Risk | Risk Management | Identification | Risk Logging | Ester Rani Ganji | P1 | Open | 2026-06-30 | 16 | 8 | 2026-06-30 | 2026-07-26 |  |  | 16 | 25
Risk | CTRL-RK002 | QB Integration - Unscoped Requirement | Control Solutions | QB Integration | Technical Risk | Risk Management | Identification | Risk Logging | Ester Rani Ganji | P1 | Open | 2026-06-20 | 8 | 4 | 2026-06-20 | 2026-08-10 |  |  | 8 | 16
CR | CTRL-CR001 | QB Integration - New Scope Addition | Control Solutions | QB Integration | Scope Addition | Change Request | Analysis | Impact Analysis | Ester Rani Ganji | P1 | Pending Approval | 2026-06-20 | 150 | 0 | 2026-06-20 | 2026-07-26
CR | CTRL-CR002 | Additional Custom Reports - 40 hrs | Control Solutions | Reports | Enhancement | Change Request | Analysis | Impact Analysis | Ester Rani Ganji | P2 | Approved | 2026-06-11 | 40 | 42 | 2026-06-11 | 2026-06-30
Task | LEV-T001 | Levata Support - Jul Tasks | Levata | Sales Cloud | Configure | Support | Development | Coding | Kailash Reddy | P2 | Completed | 2026-07-01 | 160 | 160 | 2026-07-01 | 2026-07-31
Task | LEV-T002 | Levata Support - Aug Tasks | Levata | Sales Cloud | Amend | Support | Development | Coding | Mohandasaiah Garikapati | P2 | In Progress | 2026-08-01 | 160 | 80 | 2026-08-01 | 2026-08-31
Task | LEV-T003 | SOW Amendment Coordination | Levata | Scope Management | Analyze | Project Management | Development | Coding | Ester Rani Ganji | P2 | In Progress | 2026-07-15 | 16 | 8 | 2026-07-15 | 2026-08-15
Bug | LEV-B001 | Dashboard filters not persisting across sessions | Levata | Reports | Functional | Bug Fix | Resolution | Code Fix | Kailash Reddy | P3 | Open | 2026-08-01 | 4 | 0 | 2026-08-01 | 2026-08-15
Risk | LEV-RK001 | AR Outstanding $13,160 | Levata | Financial Management | Financial Risk | Risk Management | Identification | Risk Logging | Ester Rani Ganji | P2 | Monitoring | 2026-07-01 | 8 | 4 | 2026-07-01 | 2026-08-31 |  |  | 8 | 25
Risk | LEV-RK002 | SOW Revenue Overrun | Levata | Scope Management | Scope Risk | Risk Management | Identification | Risk Logging | Ester Rani Ganji | P2 | Open | 2026-07-01 | 8 | 2 | 2026-07-01 | 2026-08-15 |  |  | 8 | 8
CR | LEV-CR001 | SOW Delta - Scope Expansion Hours | Levata | Scope Management | Scope Addition | Change Request | Analysis | Impact Analysis | Ester Rani Ganji | P2 | Pending Approval | 2026-07-15 | 160 | 0 | 2026-07-15 | 2026-08-15
Task | MED-T001 | Discovery Workshop & Stakeholder Interviews | 4Media Phase 3 | Lead Management | Analyze | Project Management | Development | Coding | Dee Reddy | P1 | Completed | 2026-06-01 | 12 | 12 | 2026-06-01 | 2026-06-03
Task | MED-T002 | BRD Review & Sign-off | 4Media Phase 3 | Lead Management | Analyze | Project Management | Development | Coding | Dhikshitha Rekulapally | P1 | Completed | 2026-06-04 | 20 | 20 | 2026-06-04 | 2026-06-10
Task | MED-T003 | Solution Design Document | 4Media Phase 3 | Lead Management | Create | Development | Development | Coding | Vasudev Irla | P1 | Completed | 2026-06-06 | 32 | 30 | 2026-06-06 | 2026-06-13
Task | MED-T004 | Salesforce Environment Setup | 4Media Phase 3 | Platform | Configure | Development | Development | Coding | Chaitanya Goriparthi | P2 | Completed | 2026-06-08 | 12 | 10 | 2026-06-08 | 2026-06-10
Task | MED-T005 | Lead Management Module Build | 4Media Phase 3 | Lead Management | Create | Development | Development | Coding | Vasudev Irla | P1 | In Progress | 2026-06-14 | 32 | 16 | 2026-06-14 | 2026-07-14
Task | MED-T006 | Campaign Configuration | 4Media Phase 3 | Campaign | Configure | Development | Development | Coding | Chaitanya Goriparthi | P2 | In Progress | 2026-06-14 | 20 | 8 | 2026-06-14 | 2026-07-08
Task | MED-T007 | New Lead Routing Flow | 4Media Phase 3 | Lead Routing | Create | Development | Development | Coding | Vasudev Irla | P1 | To Do |  | 20 | 0 | 2026-07-03 | 2026-07-24
Task | MED-T008 | UAT Test Cases Preparation | 4Media Phase 3 | UAT | Create | QA - Testing | Development | Coding | Dhikshitha Rekulapally | P2 | To Do |  | 12 | 0 | 2026-07-15 | 2026-07-29
Task | MED-T009 | Client UAT Support & Issue Resolution | 4Media Phase 3 | UAT | Test | QA - Testing | Development | Coding | Dee Reddy | P1 | To Do |  | 12 | 0 | 2026-07-29 | 2026-08-19
Task | MED-T010 | Training Material & User Guide | 4Media Phase 3 | Training | Create | Project Management | Development | Coding | Dhikshitha Rekulapally | P2 | To Do |  | 20 | 0 | 2026-08-03 | 2026-08-24
Task | MED-T011 | Go-Live Deployment & Hypercare | 4Media Phase 3 | Deployment | Deploy | Development | Development | Coding | Vasudev Irla | P1 | To Do |  | 20 | 0 | 2026-08-29 | 2026-09-13
Bug | MED-B001 | Lead routing flow crashes on empty Phone field | 4Media Phase 3 | Lead Routing | Functional | Bug Fix | Resolution | Code Fix | Vasudev Irla | P2 | Open | 2026-06-27 | 8 | 0 | 2026-06-27 | 2026-07-08
Bug | MED-B002 | Campaign member status not updating in list view | 4Media Phase 3 | Campaign | Functional | Bug Fix | Resolution | Code Fix | Chaitanya Goriparthi | P3 | Fixed | 2026-06-18 | 4 | 3 | 2026-06-18 | 2026-06-21
Risk | MED-RK001 | Tight Delivery Timeline - 260 hrs in 75 days | 4Media Phase 3 | Schedule Management | Schedule Risk | Risk Management | Identification | Risk Logging | Dee Reddy | P2 | Open | 2026-06-01 | 8 | 4 | 2026-06-01 | 2026-09-13 |  |  | 8 | 9
CR | MED-CR001 | New Lead Routing Flow - Additional Scope | 4Media Phase 3 | Lead Routing | Enhancement | Change Request | Analysis | Impact Analysis | Dee Reddy | P2 | Approved | 2026-06-23 | 30 | 0 | 2026-06-23 | 2026-07-24
Task | VRC-T001 | VRC Initial Setup & Onboarding | VRC Managed Services | Platform | Configure | Development | Development | Coding | Saikrishna Bandi | P1 | Completed | 2026-06-01 | 80 | 80 | 2026-06-01 | 2026-07-01
Task | VRC-T002 | VRC Monthly Support - Jun | VRC Managed Services | Integration | Amend | Support | Development | Coding | Sureshkumar Gidugu | P2 | Completed | 2026-06-21 | 80 | 80 | 2026-06-21 | 2026-07-20
Task | VRC-T003 | VRC Monthly Support - Jul | VRC Managed Services | Integration | Configure | Support | Development | Coding | Vishnudeep | P2 | Completed | 2026-07-21 | 80 | 80 | 2026-07-21 | 2026-08-20
Task | VRC-T004 | VRC Monthly Support - Aug | VRC Managed Services | Platform | Amend | Support | Development | Coding | Saikrishna Bandi | P2 | In Progress | 2026-08-21 | 60 | 20 | 2026-08-21 | 2026-09-20
Bug | VRC-B001 | Integration scheduler skipping weekends | VRC Managed Services | Integration | Functional | Bug Fix | Resolution | Code Fix | Saikrishna Bandi | P3 | Fixed | 2026-08-11 | 4 | 3 | 2026-08-11 | 2026-08-13
Risk | VRC-RK001 | Under-utilization - Early Stage Engagement | VRC Managed Services | Resource Management | Resource Risk | Risk Management | Identification | Risk Logging | Ester Rani Ganji | P3 | Monitoring | 2026-06-01 | 8 | 2 | 2026-06-01 | 2026-09-20 |  |  | 8 | 9

## Resources
OrbitFlow — Resource Utilization ¦ Formulas from Work Items
Sprint Cap = 136 hrs · A ≥ 90% · B 50–89% · C < 50% · Overloaded > 100%
RESOURCE MASTER (Org Roster)
Employee | Level | Manager | Role | Resource Type | Task Hrs (from Tasks) | Bug Hrs (Testing/UAT/PS) | Total Hrs | Util % | Working Cap (hrs) | Onsite/Offshore | JULY 2026 CAPACITY |  | Email | Designation | Availability % | Billing Rate ($/hr) | Joining Date | Skills | Experience (yrs)
Gopikrishna Vemuri | 1 | - | COO | Executive | [5 empty] | Onsite | Period Start | 2026-07-01 |  |  | 100
Gopinath Vedantham | 2 | Gopikrishna Vemuri | Project Lead | MGMT | [5 empty] | Onsite | Period End | 2026-07-31 |  |  | 100
Deepti Bhatt | 3 | Gopinath Vedantham | Solution Lead | Solution-Lead | [5 empty] | Offshore | Hrs / Day | 8 |  |  | 100
Murali Meruva | 3 | Gopinath Vedantham | Solution Lead | Solution-Lead | [5 empty] | Offshore | Working Days |  |  |  | 100
Amar Joshi | 3 | Gopinath Vedantham | UI Lead | UI-Lead | [5 empty] | Offshore | Full Cap (hrs) |  |  |  | 100
Jogesh Somisetti | 3 | Gopinath Vedantham | Backend Lead | Backend | [5 empty] | Offshore |  |  |  |  | 100
Lakshit Sharma | 3 | Gopinath Vedantham | Backend Lead | Backend | [5 empty] | Offshore |  |  |  |  | 100
Kishore Kumar G | 3 | Gopinath Vedantham | Backend Lead | Backend | [5 empty] | Offshore |  |  |  |  | 100
Praveen Murugesan | 3 | Gopinath Vedantham | QA Lead | QA-Lead | [5 empty] | Offshore |  |  |  |  | 100
Likhitha Vaddevalli | 4 | Deepti Bhatt | Solution Analyst | Solution | [5 empty] | Offshore |  |  |  |  | 100
Lakshmi Vaggala | 4 | Amar Joshi | UI Developer | UI | [5 empty] | Offshore |  |  |  |  | 100
Sravani Palle | 4 | Amar Joshi | UI Developer | UI | [5 empty] | Offshore |  |  |  |  | 100
Kamala Rudru | 4 | Amar Joshi | UI Developer | UI | [5 empty] | Offshore |  |  |  |  | 100
Mahendra Bhalsing | 4 | Jogesh Somisetti | Backend Developer | Backend | [5 empty] | Offshore |  |  |  |  | 100
Kapil Meshram | 4 | Jogesh Somisetti | Backend Developer | Backend | [5 empty] | Offshore |  |  |  |  | 100
Rajeshwar Thakur | 4 | Jogesh Somisetti | Backend Developer | Backend | [5 empty] | Offshore |  |  |  |  | 100
Lokesh Kundlavari | 4 | Lakshit Sharma | Backend Developer | Backend | [5 empty] | Offshore |  |  |  |  | 100
Sai Goriparti | 4 | Lakshit Sharma | Backend Developer | Backend | [5 empty] | Offshore |  |  |  |  | 100
Venkateswarlu Kanchani | 4 | Kishore Kumar G | Integration Developer | Integration | [5 empty] | Offshore |  |  |  |  | 100
Padmalochana Polaki | 4 | Kishore Kumar G | Integration Developer | Integration | [5 empty] | Offshore |  |  |  |  | 100
Konda Reddy | 4 | Kishore Kumar G | Integration Developer | Integration | [5 empty] | Offshore |  |  |  |  | 100
Aravindu Ravula | 4 | Praveen Murugesan | QA Engineer | Integration | [5 empty] | Offshore |  |  |  |  | 100
Vaibhav More | 4 | Praveen Murugesan | QA Engineer | Integration | [5 empty] | Offshore |  |  |  |  | 100
Vishwanatha Manchigegowda | 4 | Praveen Murugesan | QA Engineer | Backend | [5 empty] | Offshore |  |  |  |  | 100
Bhargava Narla | 4 | Praveen Murugesan | QA Engineer | QA | [5 empty] | Offshore |  |  |  |  | 100
Pranay Bavana | 4 | Praveen Murugesan | QA Engineer | QA | [5 empty] | Offshore |  |  |  |  | 100
Eshwar Biradar | 4 | Praveen Murugesan | QA Engineer | QA | [5 empty] | Offshore |  |  |  |  | 100
Vijayalakshmi Tonta | 4 | Praveen Murugesan | QA Engineer | QA | [5 empty] | Offshore |  |  |  |  | 100
Srija Poreddy | 4 | Praveen Murugesan | QA Engineer | QA | [5 empty] | Offshore |  |  |  |  | 100
Harshitha Mannembakam | 4 | Praveen Murugesan | QA Engineer | QA | [5 empty] | Offshore |  |  |  |  | 100
Havish Kanuri | 4 | Gopinath Vedantham | DevOps Engineer | DevOps | [5 empty] | Offshore |  |  |  |  | 100
Swati Vivek | 4 | Gopinath Vedantham | Infra Engineer | Infra | [5 empty] | Offshore |  |  |  |  | 100
Kishore Meka | 4 | Murali Meruva | Project Manager | PM |  |  |  |  | 80 | Offshore |  |  |  |  | 100
Waliu Faleye | 5 | Kishore Meka | Backend Developer | Backend |  |  |  |  | 0 | Offshore |  |  |  |  | 100
Raudha Ahmed | 5 | Kishore Meka | Backend Developer | Backend |  |  |  |  | 0 | Offshore |  |  |  |  | 100
Sreenu Bhupati | 5 | Kishore Meka | Backend Developer | Backend |  |  |  |  | 0 | Offshore |  |  |  |  | 100
Praveen Venkatesh | 5 | Kishore Meka | QA Analyst | QA |  |  |  |  | 80 | Offshore |  |  |  |  | 100
Sriram Vanumu | 4 | Jogesh Somisetti | Backend Developer | Backend | [5 empty] | Offshore |  |  |  |  | 100
Rajkumar Pichhiguntla | 4 | Lakshit Sharma | Backend Developer | Backend | [5 empty] | Offshore |  |  |  |  | 100
Janakiram Ankam | 4 | Kishore Kumar G | Integration Developer | Integration | [5 empty] | Offshore |  |  |  |  | 100
Note: Orange rows = Support Team (80 hrs capacity vs 136).

## Planned vs Actual
OrbitFlow — Planned vs Actual Effort ¦ Formulas from Work Items
Planned = Original Effort (hrs) · Actual = Actual Effort (hrs) · Variance = Planned − Actual · Source: Work Items sheet
Resource | Module (Project) | Type | Planned Hrs | Actual Hrs | Variance | Variance % | Status
Chaitanya Goriparthi | 4Media Phase 3 | Bug
Chaitanya Goriparthi | 4Media Phase 3 | Task
Dee Reddy | 4Media Phase 3 | Task
Dhikshitha Rekulapally | 4Media Phase 3 | Task
Vasudev Irla | 4Media Phase 3 | Bug
Vasudev Irla | 4Media Phase 3 | Task
Akhil Kotagiri | Control Solutions | Bug
Akhil Kotagiri | Control Solutions | Task
Ester Rani Ganji | Control Solutions | Task
Jeevan Babu Paruchuri | Control Solutions | Task
Nagarjuna Reddy Sadhu | Control Solutions | Bug
Nagarjuna Reddy Sadhu | Control Solutions | Task
Seeham Saber Hussain | Control Solutions | Task
Sureshkumar Gidugu | Control Solutions | Bug
Sureshkumar Gidugu | Control Solutions | Task
Tejaswini Reddy Tamma | Control Solutions | Task
Vishnudeep | Control Solutions | Bug
Vishnudeep | Control Solutions | Task
Prateek Shinde | GCI Phase 1 | Task
Sudhakar Reddy Lekkala | GCI Phase 1 | Bug
Sudhakar Reddy Lekkala | GCI Phase 1 | Task
Ester Rani Ganji | Levata | Task
Kailash Reddy | Levata | Bug
Kailash Reddy | Levata | Task
Mohandasaiah Garikapati | Levata | Task
Saikrishna Bandi | VRC Managed Services | Bug
Saikrishna Bandi | VRC Managed Services | Task
Sureshkumar Gidugu | VRC Managed Services | Task
Vishnudeep | VRC Managed Services | Task
TOTAL

## Risk Register
OrbitFlow — Risk Register ¦ All risks also in Work Items (Type=Risk)
Risk Score = Probability × Impact · Critical ≥ 15 ¦ High ≥ 10 ¦ Medium ≥ 5 ¦ Low < 5
Type | ID | Project | Risk Description | Module | SubModule | Risk Category | Assigned To | Priority | Status | Risk Score | Target Date | Mitigation Hrs

## Change Requests
OrbitFlow — Change Requests ¦ All CRs also in Work Items (Type=CR)
CR Status: Approved = included in sprint · Pending Approval = awaiting sign-off · Rejected = not proceeding
Type | ID | CR Description | Module | SubModule | CR Category | Requested By | Priority | Status | CR Date | Target Date | Planned Hrs | Actual Hrs

## Financial Tracker
OrbitFlow — Financial Tracker
EV ($) = (SOW Hrs − Actual Hrs) × Blended Rate · Actual Hrs pulled from Work Items (Type=Task, Actual Effort)
Project ID | Project Name | SOW Amount ($) | Invoiced ($) | Received ($) | AR Outstanding ($) | SOW Pending ($) | SOW Hrs | Actual Hrs (from WI) | Blended Rate ($/hr) | EV ($) | Project Type
TOTAL

## Projects Master
OrbitFlow — Projects Master ¦ Lookup source for all sheets
Project Name in column B must match Module column in Work Items exactly · SOW Hrs = contracted effort hours
Project ID | Project Name | PM | Account Manager | Project Type | Status | Start Date | End Date | SOW Hrs | Domain | SOW Value ($) | Priority | Health | Business Unit | Delivery Manager | Technology | Currency | Description
P001 | GCI Phase 1 | Gopinath Vedantham | Gopikrishna Vemuri | Fixed Monthly Block of Hours | Active | 2025-01-01 | 2025-12-31 | 3840 | Telecommunications | 460800 | Medium | Green |  |  |  | USD
P002 | Control Solutions | Deepti Bhatt | Gopikrishna Vemuri | One Time - Implementation | Active | 2025-02-19 | 2025-03-31 | 1018 | Manufacturing | 89800 | Medium | Green |  |  |  | USD
P003 | Levata | Deepti Bhatt | Gopikrishna Vemuri | Fixed Monthly Block of Hours | Active | 2024-06-12 | 2025-08-31 | 8640 | Business Consulting | 171600 | Medium | Green |  |  |  | USD
P004 | 4Media Phase 3 | Murali Meruva | Gopikrishna Vemuri | One Time - Implementation | Active | 2025-06-18 | 2025-09-30 | 370 | PR & Communications | 26036 | Medium | Green |  |  |  | USD
P005 | VRC Managed Services | Praveen Venkatesh | Gopikrishna Vemuri | Fixed Monthly Block of Hours | Active | 2025-05-12 | 2026-05-11 | 1200 | Information Management | 178800 | Medium | Green |  |  |  | USD

## CONFIG
OrbitFlow — Configuration & Rate Card
▸ Sprint Assumptions
Working Days/Month | 20 | Standard (20 business days)
Hours/Day | 8
Hours/Month |  | Used in all utilization calculations
Sprint Cap (hrs/resource) | 136 | From reference tracker
▸ Rate Card ($/hr)
Role | Onsite ($/hr) | Offshore ($/hr) | Notes
Project Manager | 75 | 32
Solution Architect | 90 | 38
Senior Developer | 70 | 28
Developer | 60 | 22
QA Engineer | 55 | 18
Business Analyst | 60 | 20
Admin / Support | 50 | 15
Blended Rate | 65 | 25 | Weighted average for mixed teams
▸ Project Registry (for reference)
Project ID | Module Name (Work Items) | PM

## LookUp Master
Time Tracking-TASK |  | Project Tracking -TASK
Activity | SubActivity | Activity | SubActivity
Others | Leave | Development | POC/ Research
| Research and Development |  | Coding
| Corp-Facilities |  | Technical discusion
| Corp-Payroll and Benefits |  | CodeRework
| Knowledge Sharing Sessions |  | CodeReview
| Travel Coordination |  | UnitTesting
| Strategy & Planning |  | SFDCAdministration
| Company Meeting |  | Build & Deployment
Management Meeting
|  | Testing | Identify & Analysis
Trainings | Training - Provided |  | Retesting
| Training - Attended |  | Executing TC/TS (Testing)
| Training-Self Learning |  | Regression testing
| Training-Teams |  | Creating TC/TS (Testing)
| Training-Certifications (Target) |  | QA-ArtifactsReview
| Training-Technical Guidance |  | QA-ArtifactsRework
Process Adherence | Process-Audit | Requirements | Requirement Analysis
| Process-CMAudit |  | Requirement Clarifications(Q&A)
| Process-Project Health Reports |  | Creating Functional requirements
| Process-Reporting | Design | LLD/DB Design
| Process-Trainings |  | HLD
PreSales | Presales-Proposal Preparation | Documentation | User Guides
| Presales-Estimation |  | Training Material
| Presales-Requirement Analysis/Gathering |  | Installation Guide
PreSales Calls
|  | ProjectManagement | Estimations(CR/NewReq)
Sales | Lead Generation |  | Team Leading activities
| Cold Calls |  | PM Calls
| Account Management (Project Health, etc) |  | Sprint Planning
| Prospect Followup |  | Process Audits
Marketing | Branding | Customer Communication | Calls
| Website Updation |  | Demo & Feedback
| Content Management |  | Code Walkthru
HR | HR-Appraisal | UAT | Identify & Analysis
| HR-EventManagement |  | Retesting
| HR-Induction |  | Support
| HR-Performance Management |  | System Testing(Customer Env)
HR-Resource Mentoring
| Recruitment | ProductionSupport | Support
| HR-Attend Conferences |  | Rollout/Migration/Deployment
Checklist Preparation
|  | Implementation | Installation and Configuration
Product Training
Product Demo
Customer Communication(Calls/Emails)
Offshore Communication
Artifacts Documentation
Post Implementation Testing
|  | KnowledgeTransfer | KT-Provided
KT-Attended

## Drill-Down
OrbitFlow — Work Items Drill-Down ¦ Click a count on the Project Dashboard to jump here
ID | Summary | Assigned To | Priority | Status | Start | End
| Monthly Support - Case Management & Config | Prateek Shinde | P2 | Completed | 2026-07-01 | 2026-07-15
GCI-T002 | Monthly Support - Field Service Optimization | Sudhakar Reddy Lekkala | P2 | Completed | 2026-07-16 | 2026-07-31
GCI-T003 | Monthly Support - API Integration Review | Sudhakar Reddy Lekkala | P2 | In Progress | 2026-08-01 | 2026-08-31
GCI-T004 | Canada Holiday Buffer - Aug Support Hours | Prateek Shinde | P3 | In Progress | 2026-08-15 | 2026-08-31
ID | Summary | Assigned To | Priority | Status | Start | End
| API timeout on bulk sync over 5000 records | Sudhakar Reddy Lekkala | P2 | Monitoring | 2026-07-20 | 2026-08-31
ID | Summary | Assigned To | Priority | Status | Start | End
| Timezone Coordination Gap - Canada Team | Gopikrishna Vemuri | P2 | Open | 2026-07-01 | 2026-09-30
GCI-RK002 | New Client Requirements Mid-Engagement | Gopikrishna Vemuri | P3 | Open | 2026-07-01 | 2026-12-31
ID | Summary | Assigned To | Priority | Status | Start | End
| Canada Holiday Buffer Hours | Gopikrishna Vemuri | P3 | Approved | 2026-08-01 | 2026-08-31
ID | Summary | Assigned To | Priority | Status | Start | End
| Requirements & BRD Review | Ester Rani Ganji | P1 | Completed | 2026-06-01 | 2026-06-03
CTRL-T002 | Salesforce Org Setup & Config | Jeevan Babu Paruchuri | P1 | Completed | 2026-06-04 | 2026-06-10
CTRL-T003 | Data Model Design - Custom Objects | Akhil Kotagiri | P1 | Completed | 2026-06-04 | 2026-06-11
CTRL-T004 | Integration Architecture Blueprint | Sureshkumar Gidugu | P2 | Completed | 2026-06-07 | 2026-06-13
CTRL-T005 | Security & Permission Set Design | Nagarjuna Reddy Sadhu | P2 | Completed | 2026-06-07 | 2026-06-10
CTRL-T006 | FSL Work Orders & Service Appointments | Vishnudeep | P1 | Completed | 2026-06-11 | 2026-06-20
CTRL-T007 | Service Cloud Case Management | Seeham Saber Hussain | P1 | Completed | 2026-06-11 | 2026-06-17
CTRL-T008 | QB Integration - Design Phase | Sureshkumar Gidugu | P1 | In Progress | 2026-06-18 | 2026-07-11
CTRL-T009 | UAT Test Plan Creation | Tejaswini Reddy Tamma | P2 | Completed | 2026-06-15 | 2026-06-18
CTRL-T010 | Custom Report Development - 40 hrs | Nagarjuna Reddy Sadhu | P3 | Completed | 2026-06-20 | 2026-06-30
CTRL-T011 | UAT Execution & Client Sign-off | Tejaswini Reddy Tamma | P1 | In Progress | 2026-06-30 | 2026-07-11
CTRL-T012 | QB Integration - Development | Sureshkumar Gidugu | P1 | Blocked | 2026-06-25 | 2026-07-26
CTRL-T013 | Bug Fixes Round 1 | Jeevan Babu Paruchuri | P1 | In Progress | 2026-06-30 | 2026-07-11
CTRL-T014 | Go-Live Preparation & Checklist | Ester Rani Ganji | P1 | To Do | 2026-07-12 | 2026-07-18
CTRL-T015 | Production Deployment | Akhil Kotagiri | P1 | To Do | 2026-07-18 | 2026-07-21
ID | Summary | Assigned To | Priority | Status | Start | End
| FSL Work Order not auto-creating Service Appointment | Vishnudeep | P1 | Fixed | 2026-06-18 | 2026-06-21
CTRL-B002 | QB sync creating duplicate invoice records | Sureshkumar Gidugu | P1 | In Progress | 2026-06-22 | 2026-07-11
CTRL-B003 | Custom report date filter ignoring timezone offset | Nagarjuna Reddy Sadhu | P3 | Open | 2026-06-28 | 2026-07-11
CTRL-B004 | Permission set missing field access for Service Manager | Akhil Kotagiri | P2 | Fixed | 2026-06-29 | 2026-06-30
ID | Summary | Assigned To | Priority | Status | Start | End
| Effort Overrun - 107 Hours | Ester Rani Ganji | P1 | Open | 2026-06-30 | 2026-07-26
CTRL-RK002 | QB Integration - Unscoped Requirement | Ester Rani Ganji | P1 | Open | 2026-06-20 | 2026-08-10
ID | Summary | Assigned To | Priority | Status | Start | End
| QB Integration - New Scope Addition | Ester Rani Ganji | P1 | Pending Approval | 2026-06-20 | 2026-07-26
CTRL-CR002 | Additional Custom Reports - 40 hrs | Ester Rani Ganji | P2 | Approved | 2026-06-11 | 2026-06-30
ID | Summary | Assigned To | Priority | Status | Start | End
| Levata Support - Jul Tasks | Kailash Reddy | P2 | Completed | 2026-07-01 | 2026-07-31
LEV-T002 | Levata Support - Aug Tasks | Mohandasaiah Garikapati | P2 | In Progress | 2026-08-01 | 2026-08-31
LEV-T003 | SOW Amendment Coordination | Ester Rani Ganji | P2 | In Progress | 2026-07-15 | 2026-08-15
ID | Summary | Assigned To | Priority | Status | Start | End
| Dashboard filters not persisting across sessions | Kailash Reddy | P3 | Open | 2026-08-01 | 2026-08-15
ID | Summary | Assigned To | Priority | Status | Start | End
| AR Outstanding $13,160 | Ester Rani Ganji | P2 | Monitoring | 2026-07-01 | 2026-08-31
LEV-RK002 | SOW Revenue Overrun | Ester Rani Ganji | P2 | Open | 2026-07-01 | 2026-08-15
ID | Summary | Assigned To | Priority | Status | Start | End
| SOW Delta - Scope Expansion Hours | Ester Rani Ganji | P2 | Pending Approval | 2026-07-15 | 2026-08-15
ID | Summary | Assigned To | Priority | Status | Start | End
| Discovery Workshop & Stakeholder Interviews | Dee Reddy | P1 | Completed | 2026-06-01 | 2026-06-03
MED-T002 | BRD Review & Sign-off | Dhikshitha Rekulapally | P1 | Completed | 2026-06-04 | 2026-06-10
MED-T003 | Solution Design Document | Vasudev Irla | P1 | Completed | 2026-06-06 | 2026-06-13
MED-T004 | Salesforce Environment Setup | Chaitanya Goriparthi | P2 | Completed | 2026-06-08 | 2026-06-10
MED-T005 | Lead Management Module Build | Vasudev Irla | P1 | In Progress | 2026-06-14 | 2026-07-14
MED-T006 | Campaign Configuration | Chaitanya Goriparthi | P2 | In Progress | 2026-06-14 | 2026-07-08
MED-T007 | New Lead Routing Flow | Vasudev Irla | P1 | To Do | 2026-07-03 | 2026-07-24
MED-T008 | UAT Test Cases Preparation | Dhikshitha Rekulapally | P2 | To Do | 2026-07-15 | 2026-07-29
MED-T009 | Client UAT Support & Issue Resolution | Dee Reddy | P1 | To Do | 2026-07-29 | 2026-08-19
MED-T010 | Training Material & User Guide | Dhikshitha Rekulapally | P2 | To Do | 2026-08-03 | 2026-08-24
MED-T011 | Go-Live Deployment & Hypercare | Vasudev Irla | P1 | To Do | 2026-08-29 | 2026-09-13
ID | Summary | Assigned To | Priority | Status | Start | End
| Lead routing flow crashes on empty Phone field | Vasudev Irla | P2 | Open | 2026-06-27 | 2026-07-08
MED-B002 | Campaign member status not updating in list view | Chaitanya Goriparthi | P3 | Fixed | 2026-06-18 | 2026-06-21
ID | Summary | Assigned To | Priority | Status | Start | End
| Tight Delivery Timeline - 260 hrs in 75 days | Dee Reddy | P2 | Open | 2026-06-01 | 2026-09-13
ID | Summary | Assigned To | Priority | Status | Start | End
| New Lead Routing Flow - Additional Scope | Dee Reddy | P2 | Approved | 2026-06-23 | 2026-07-24
ID | Summary | Assigned To | Priority | Status | Start | End
| VRC Initial Setup & Onboarding | Saikrishna Bandi | P1 | Completed | 2026-06-01 | 2026-07-01
VRC-T002 | VRC Monthly Support - Jun | Sureshkumar Gidugu | P2 | Completed | 2026-06-21 | 2026-07-20
VRC-T003 | VRC Monthly Support - Jul | Vishnudeep | P2 | Completed | 2026-07-21 | 2026-08-20
VRC-T004 | VRC Monthly Support - Aug | Saikrishna Bandi | P2 | In Progress | 2026-08-21 | 2026-09-20
ID | Summary | Assigned To | Priority | Status | Start | End
| Integration scheduler skipping weekends | Saikrishna Bandi | P3 | Fixed | 2026-08-11 | 2026-08-13
ID | Summary | Assigned To | Priority | Status | Start | End
| Under-utilization - Early Stage Engagement | Ester Rani Ganji | P3 | Monitoring | 2026-06-01 | 2026-09-20
ID | Summary | Assigned To | Priority | Status | Start | End

## Billing Milestones
OrbitFlow — Billing Milestones & Schedule
Billing model by Project Type · Fixed Bid = milestone % of SOW · Fixed Monthly = team price × months · T&M = hours × rate · Rates from CONFIG
Project ID | Project Name | Project Type | Billing Model | SOW Value ($) | Scheduled Billing ($)
0
FIXED BID — MILESTONE BILLING (One-Time Implementation)
Project | Milestone | % of SOW | Amount ($) | Status
P002 | Kickoff | 30% |  | Pending
P002 | Development Complete | 40% |  | Pending
P002 | UAT Signoff | 20% |  | Pending
P002 | Project Signoff | 10% |  | Pending
P004 | Kickoff | 30% |  | Pending
P004 | Development Complete | 40% |  | Pending
P004 | UAT Signoff | 20% |  | Pending
P004 | Project Signoff | 10% |  | Pending
FIXED MONTHLY — TEAM-BASED PRICING (editable count & location per project)
Role | Count | Location | Rate ($/hr) | Hrs/Month | Monthly ($)
Project Manager | 0.5 | Onsite
Developer | 2 | Offshore
QA Engineer | 1 | Offshore
Business Analyst | 0.5 | Onsite
Monthly Price ($)
Contract Months (SOW Hrs ÷ 160)
Contract Value ($)
Role | Count | Location | Rate ($/hr) | Hrs/Month | Monthly ($)
Project Manager | 0.5 | Onsite
Developer | 2 | Offshore
QA Engineer | 1 | Offshore
Business Analyst | 0.5 | Onsite
Monthly Price ($)
Contract Months (SOW Hrs ÷ 160)
Contract Value ($)
Role | Count | Location | Rate ($/hr) | Hrs/Month | Monthly ($)
Project Manager | 0.5 | Onsite
Developer | 2 | Offshore
QA Engineer | 1 | Offshore
Business Analyst | 0.5 | Onsite
Monthly Price ($)
Contract Months (SOW Hrs ÷ 160)
Contract Value ($)
T&M — TIME & MATERIALS (no active project)
Billing = Hours × Rate. Use CONFIG onsite/offshore rate by role: = Hours × VLOOKUP(Role, CONFIG!$A$11:$C$18, 2=Onsite¦3=Offshore, 0)

## Resource Cost
OrbitFlow — Resource Cost & Cost-Benefit
Cost per resource by level (₹ Lakhs) → USD · Margin = bill potential (rate × hrs/month) − cost · Rates from CONFIG
ASSUMPTIONS |  |  | Level | Annual Cost (₹L) | [7 empty] | Roster Role | Rate Card Role
FX (₹ per $) | 83 |  | 1 | 36 | [7 empty] | COO | Solution Architect
Hrs / Month |  |  | 2 | 24 | [7 empty] | Project Lead | Project Manager
Blended Cost ($/hr) |  |  | 3 | 24 | [7 empty] | Project Manager | Project Manager
Lakh (₹) | 100000 |  | 4 | 12 | [7 empty] | Solution Lead | Solution Architect
|  |  | 5 | 12 | [7 empty] | Solution Analyst | Business Analyst
[12 empty] | UI Lead | Senior Developer
Employee | Level | Role | Onsite/Offshore | Rate Card Role | Bill Rate ($/hr) | Annual Cost (₹L) | Annual Cost ($) | Monthly Cost ($) | Monthly Bill Potential ($) | Monthly Margin ($) | Margin % | Backend Lead | Senior Developer
[12 empty] | QA Lead | QA Engineer
[12 empty] | UI Developer | Developer
[12 empty] | Backend Developer | Developer
[12 empty] | Integration Developer | Developer
[12 empty] | QA Engineer | QA Engineer
[12 empty] | QA Analyst | QA Engineer
[12 empty] | DevOps Engineer | Developer
[12 empty] | Infra Engineer | Admin / Support
PROJECT COST-BENEFIT
Project | SOW $ (Revenue) | Actual Hrs | Cost Rate ($/hr)